Sprint 8 Product Backlog

Team Name: SAVR x ASU CSE Capstone

Team Members: Aashir Javed, Peter Forbes, Alex Wei

Sprint: Sprint 8

Sprint Dates: September 28 – October 12

Taiga Board URL: https://tree.taiga.io/project/peteyjoe-savr-asu-cse-capstone/taskboard/sprint-8-2782

Sponsor / Product Owner: David D’Agostino

Product Owner/Client Approval

Review the revised Sprint 8 plan with the sponsor, clarify the backend API changes and access requirements, discuss the B2B dashboard, and secure approval of any necessary scope adjustments.

- Topics for Customer/Product Owner Discussion:

  - A sponsor meeting is still needed to review Sprint 7 outcomes and confirm the revised Sprint 8 plan.

  - The Expo migration is almost complete and all screens have been ported. Backend API changes still need to be implemented and tested, but the team does not yet have access to the updated API.

  - The team is no longer targeting production in Sprint 8. The proposed focus is app refinement, cross-platform testing, and implementation of the API changes once access is available.

  - The B2B dashboard discovery meeting has not taken place. The sponsor discussion must clarify its requirements and priorities before dashboard design or implementation proceeds.

  - The revised backlog below is proposed for sponsor review. Approval of the revised scope and any API or B2B decisions remains pending.

- Approval:

  - Customer/Product Owner Name: David D’Agostino

  - Customer/Product Owner Signature:

Please look at next page for details on User Stories, and Tasks.

1. Sprint Overview

Sprint 7 made substantial progress on the Expo migration, with all screens ported. The migration is almost complete, but backend API changes still require implementation and validation. We do not yet have access to the updated API and need to discuss the changes with our sponsor. The B2B dashboard meeting also remains outstanding.

Sprint 8 will focus on refining and testing the app, completing the remaining migration work, and implementing the API changes as access becomes available. The team will meet with the sponsor to clarify the backend changes and discuss the B2B dashboard. Production submission and launch are deferred beyond this sprint.

The expected outcome is a more stable app, progress on API compatibility, and documented sponsor decisions and remaining dependencies.

2. Sprint Planning Agenda

The following agenda will guide the revised Sprint 8 planning discussion:

- Context and goal of the meeting

- Review Sprint 7 progress and outstanding work

- Clarify backend API changes and obtain access to the updated API

- Discuss B2B dashboard requirements and priorities with the sponsor

- Define Sprint 8 priorities

- Review and confirm Sprint 8 backlog items

- Break user stories into actionable tasks

- Review risks and feasibility

- Assign user stories and tasks

- Confirm acceptance criteria and test scenarios

- Obtain Product Owner agreement on the revised scope

3. Sprint Goal

Continue refining and testing the Expo app on iOS and Android, complete the remaining integration work, and implement the backend API changes once access is provided. Meet with the sponsor to resolve API questions and discuss the B2B dashboard. By the end of Sprint 8, completed work should be validated and any remaining blocked work documented with clear next steps. Production release is not a Sprint 8 goal.

4. Project Epics

No new epics are proposed. Sprint 8 work is concentrated in Mobile App Foundation and Core UX, Research, Integration, and Technical Validation, and Quality Assurance and Testing, with B2B Partner Platform discovery pending the sponsor discussion. Release Engineering and Deployment remains a longer-term epic; production submission is deferred.

- Authentication and Account System

- Mobile App Foundation and Core UX

- Research, Integration, and Technical Validation

- Release Engineering and Deployment

- Quality Assurance and Testing

- B2B Partner Platform

5. Sprint Backlog Items

User Story 1

As a SAVR mobile user, I want the app’s core flows tested and refined on both platforms so that the Expo version is reliable while API integration work continues.

- Priority: Critical

- Epic: Quality Assurance and Testing

- Assigned To: Aashir Javed

- Effort: 12 points

- Current Status: New

Tasks

- Task 1: Run a full regression pass across both platforms

  - Description: Test core flows on iOS and Android after the screen ports. Record pass, fail, or blocked results, identifying checks that require the updated backend API.

  - Expected Effort: 4

  - Assigned To: Aashir Javed

  - Status: New

- Task 2: Fix crash and stability issues found during regression testing

  - Description: Resolve crashes, freezes, and broken states found during regression testing, prioritizing authentication, chat, and lists. Track issues that require API access separately.

  - Expected Effort: 4

  - Assigned To: Aashir Javed

  - Status: New

- Task 3: Expand tests for the changed backend API

  - Description: Update integration tests and error-handling checks against the sponsor-confirmed API contract. Prepare test cases while access is pending and run them against the updated API once available.

  - Expected Effort: 2

  - Assigned To: Aashir Javed

  - Status: New

- Task 4: Retest fixes and document remaining blockers

  - Description: Verify the highest-priority fixes on both platforms and document unresolved defects and any tests blocked by API access.

  - Expected Effort: 2

  - Assigned To: Aashir Javed

  - Status: New

Test Scenarios

- Core flows including authentication, chat, lists, flyers, and stores are tested on both iOS and Android; API-dependent checks are marked blocked when access is unavailable.

- The app does not crash during normal use across either platform.

- Changed API responses and error states are covered by test cases based on the confirmed contract.

- High-severity fixes are retested on both platforms and unresolved issues are documented.

Test Acceptance Criteria

- At least 8 core flows have recorded regression results on both platforms, with each result marked pass, fail, or blocked and supported by notes.

- Known crash bugs in testable core flows are fixed and verified, or documented with an owner and next step if unresolved.

- Each sponsor-confirmed API change has a corresponding integration test or documented test case; execution blockers are recorded.

- Every high-severity defect found during the sprint has a severity, owner, and verified fix or documented follow-up.

- No new regressions are introduced by any bug fix made during the sprint.

Status of Test Criteria

- Cross platform regression pass: Not started

- Crash and stability fix verification: Not started

- Updated API test coverage: Awaiting API clarification and access

- Fix verification and blocker review: Not started

User Story 2

As a SAVR development team, we want the Expo app updated to match the changed backend API so that the remaining migration work can be completed and validated on iOS and Android.

- Priority: Critical

- Epic: Research, Integration, and Technical Validation

- Assigned To: Peter Forbes

- Effort: 13 points

- Current Status: New

Tasks

- Task 1: Clarify API changes and obtain backend access

  - Description: Meet with the sponsor to review changed endpoints, request and response formats, authentication requirements, and access to the updated API. Document agreed requirements and unresolved questions.

  - Expected Effort: 3

  - Assigned To: Peter Forbes

  - Status: New

- Task 2: Update the app’s API client and affected screens

  - Description: Once the API contract and access are available, update requests, response handling, and affected screen behavior. Keep the remaining Expo integration work aligned with the updated backend.

  - Expected Effort: 3

  - Assigned To: Peter Forbes

  - Status: Blocked pending API clarification and access

- Task 3: Validate API integration across iOS and Android

  - Description: Exercise affected flows against the updated backend on both platforms and resolve integration differences with support from the testing work in User Story 1.

  - Expected Effort: 4

  - Assigned To: Peter Forbes

  - Status: Blocked pending API access and implementation

- Task 4: Complete remaining Expo migration refinements

  - Description: Review the ported screens, fix remaining migration issues that can be addressed now, and document any work still blocked by the API changes.

  - Expected Effort: 3

  - Assigned To: Peter Forbes

  - Status: New

Test Scenarios

- Updated API requests and responses match the sponsor-confirmed contract.

- Affected screens handle successful responses, loading states, and API errors correctly.

- API-dependent flows behave consistently on iOS and Android when tested against the updated backend.

- All ported screens remain usable after integration changes, with blocked flows clearly documented.

Test Acceptance Criteria

- The sponsor meeting records API changes, access requirements, and agreed next steps. If access remains unavailable, the dependency and follow-up owner are documented.

- Each accessible, agreed API change is implemented; any unimplemented change is listed with its blocker and next step.

- Implemented API changes are validated on both platforms with recorded results.

- Remaining Expo migration issues are fixed and retested or recorded with an owner and follow-up plan.

- No affected flow is marked complete while its required API integration or validation remains blocked.

Status of Test Criteria

- Sponsor API discussion and access: Pending

- API client updates: Blocked pending clarification and access

- Cross-platform integration validation: Blocked pending access and implementation

- Remaining Expo migration refinement: Not started

User Story 3

As a SAVR project team, we want the mobile experience refined and the B2B dashboard scope clarified with our sponsor so that usability work continues and future dashboard work follows agreed requirements.

- Priority: High

- Epic: Mobile App Foundation and Core UX; B2B Partner Platform

- Assigned To: Alex Wei

- Effort: 9 points

- Current Status: New

Tasks

- Task 1: Prepare and hold the B2B dashboard sponsor discussion

  - Description: Arrange the outstanding sponsor discussion, prepare questions about intended users and dashboard needs, and record decisions and unresolved questions.

  - Expected Effort: 2

  - Assigned To: Alex Wei

  - Status: New

- Task 2: Document B2B requirements and follow-up work

  - Description: Translate the sponsor discussion into an initial requirements summary and prioritized follow-up items. Prepare initial wireframes only if the scope is sufficiently clear.

  - Expected Effort: 2

  - Assigned To: Alex Wei

  - Status: Blocked pending B2B sponsor discussion

- Task 3: Review usability across the ported screens

  - Description: Walk through the Expo screens on iOS and Android, gather team feedback, and log visual and usability issues in one shared list.

  - Expected Effort: 2

  - Assigned To: Alex Wei

  - Status: New

- Task 4: Refine the highest-priority UI issues

  - Description: Fix the most important visual and usability issues identified in the screen review and verify improvements on both platforms.

  - Expected Effort: 3

  - Assigned To: Alex Wei

  - Status: New

Test Scenarios

- The sponsor discussion clarifies intended B2B users, dashboard needs, and open questions.

- B2B decisions are captured in a requirements summary with clear follow-up items.

- Ported screens are reviewed for layout and usability on both platforms.

- UI fixes are rechecked on iOS and Android.

Test Acceptance Criteria

- The B2B meeting is held and notes are recorded; if scheduling prevents it, the pending questions and follow-up owner are documented.

- An initial B2B requirements summary reflects the sponsor discussion, with unresolved decisions explicitly identified.

- All ported screens receive a visual and usability review with findings logged in one shared list.

- The highest-priority UI issues are fixed and verified, or documented with an owner and next step.

- No B2B requirements or wireframes are treated as sponsor-approved before the outstanding discussion and review.

Status of Test Criteria

- B2B sponsor discussion: Pending

- B2B requirements summary: Blocked pending discussion

- Cross-platform usability review: Not started

- UI issue fix verification: Not started

6. Task Breakdown and Assignment

Tasks are assigned based on each member’s current development and design responsibilities:

- Peter Forbes owns API integration and the remaining Expo migration refinements, continuing from the screen-porting and cross-platform work in Sprint 7.

- Aashir Javed owns regression testing, stability fixes, and API test coverage, continuing from backend hardening and testing work.

- Alex Wei owns the B2B sponsor discussion and requirements summary, along with usability reviews and UI refinement.

Current task distribution: Aashir 4 tasks, Peter 4 tasks, Alex 4 tasks.

This keeps the workload even across the team and satisfies the rubric expectation of 3 to 5 tasks per member.

7. Effort Estimation

The effort estimates for Sprint 8 are:

- User Story 1 (Aashir): 12 points

- User Story 2 (Peter): 13 points

- User Story 3 (Alex): 9 points

Total Sprint Points: 34 points

The 34 points are proposed effort estimates, not a comparison with verified Sprint 7 velocity. Peter’s 13-point story covers API clarification, implementation, and migration refinement. Aashir’s 12-point story covers cross-platform regression and API tests. Alex’s 9-point story covers B2B discovery and UI refinement. Implementation and validation depend on sponsor clarification and backend access; scope may need adjustment if those dependencies remain unresolved.

8. Progress Tracking and Status Updates

Sprint 8 progress is tracked in Taiga and updated throughout the sprint.

Current board setup includes:

- User stories: 3

- Tasks: 12

- Epics: 6

- Status categories: New, In Progress, Ready for Test, Closed

Progress updates will distinguish work that can proceed from work blocked by sponsor discussions or API access. Blocked items will include the dependency, owner, and next follow-up so the team can continue available refinement and testing work.

9. Risk Management

Risk 1: Access to the updated backend API remains unavailable

- Likelihood: High

- Impact: High

- Description: The team does not yet have access to backend API changes. Continued lack of access can prevent implementation and validation of affected flows.

- Mitigation Strategy: Prioritize the sponsor meeting and access request early. Prepare integration changes and tests from the confirmed contract where possible, and continue work on unaffected flows while blocked.

Risk 2: API changes require more rework than expected

- Likelihood: Medium

- Impact: High

- Description: Changed endpoints or data formats may require updates across several ported screens and reveal additional integration issues.

- Mitigation Strategy: Document the changed API contract before implementation, map affected flows, and test updates incrementally on both platforms.

Risk 3: Cross-platform testing reveals stability issues

- Likelihood: Medium

- Impact: High

- Description: Ported screens may expose crashes or platform-specific behavior during regression testing, increasing the remaining refinement work.

- Mitigation Strategy: Test core flows early, prioritize severe defects, and retest fixes on iOS and Android before marking tasks complete.

Risk 4: The B2B sponsor meeting is delayed

- Likelihood: Medium

- Impact: Medium

- Description: The B2B dashboard meeting has not taken place. Scheduling delays can leave requirements unclear and block the requirements summary.

- Mitigation Strategy: Arrange the discussion early and prepare focused questions. Record unresolved decisions and defer scope-dependent dashboard work until the sponsor clarifies requirements.

Risk 5: API and B2B discussions expand the sprint scope

- Likelihood: Medium

- Impact: Medium

- Description: Sponsor discussions may introduce additional API or dashboard requirements beyond the team’s capacity for this sprint.

- Mitigation Strategy: Prioritize required API compatibility and core app reliability. Record additional requests in the backlog and confirm priorities with the sponsor before committing to more work.

Risk Monitoring Plan

- Review sprint risks during standups

- Log blockers in Taiga as sprint issues when they appear

- Follow up on sponsor meeting scheduling and API access early in the sprint

- Review test results and unresolved API dependencies throughout the sprint

10. Notes on Project Management Software

All Sprint 8 backlog items, tasks, assignments, statuses, and priorities are documented in Taiga. The sprint board reflects:

- user stories tied to the sprint goal

- assigned tasks for each team member

- effort points

- status updates, including sponsor and API dependencies

- backlog alignment with app refinement, technical integration, testing, and B2B discovery

This supports transparency, accountability, and continuous sprint tracking throughout Sprint 8.

Thank you.