Sprint 7 Product Backlog

Team Name: SAVR x ASU CSE Capstone

Team Members: Aashir Javed, Peter Forbes, Alex Wei

Sprint: Sprint 7

Sprint Dates: 31 Aug 2026 to 14 Sep 2026

Taiga Board URL: https://tree.taiga.io/project/peteyjoe-savr-asu-cse-

capstone/taskboard/sprint-6-4209

Sponsor / Product Owner: David D’Agostino

## Product Owner/Client Approval

Discuss the plan to the customer/product owner. Make any necessary adjustments based on the discussion and secure their approval to proceed.

- Customer/Product Owner Feedback for Sprint Planning:

  - We met with the Product Owner to review Sprint 6 outcomes and align on the Sprint 7 plan.

  - Sprint 6 was completed in full. The remaining backend integrations were wired up, the testing environment is running, the Expo migration is nearly complete, and the App Store assets are in progress. The discussion focused on finishing the Expo migration, getting a working Android build running, and continuing App Store and Play Store preparation.

  - We also raised the idea of a feature freeze once Sprint 7 wraps, so the team can move into stabilization and launch prep without new scope being added. The Product Owner agreed this made sense and said we can lock it in once Android is confirmed working.

  - We clarified that the B2B dashboard stays in discovery only for now, meaning requirements gathering and wireframes, not implementation, so it does not compete with the launch timeline. The Product Owner agreed with this scoping.

  - The Sprint 7 backlog was reviewed with the Product Owner. The selected backlog items, priorities, assigned work, and sprint focus were discussed and approved for the upcoming sprint.

- Approval:

  - Customer/Product Owner Name: David D’Agostino

  - Customer/Product Owner Signature:

  - Date: __________________________

Please look at next page for details on User Stories, and Tasks.

1. Sprint Overview

Sprint 6 closed out fully. The backend integrations that had been blocked since last semester got wired up, the testing environment is running against the core flows, the Expo migration pushed close to complete, and the first round of App Store assets came together. That puts us in a strong position heading into Sprint 7.

Sprint 7 is about finishing what Sprint 6 started on the platform side. The main goal is getting the Expo migration fully done and getting a working Android build running for the first time, which has been the target since we moved off SwiftUI. In parallel, we are pushing App Store prep further and starting Play Store prep now that Android is becoming real, and beginning discovery work on the B2B dashboard so it does not sit untouched until later in the semester.

This sprint also sets up the feature freeze conversation with the Product Owner. Once Android is confirmed working, the plan is to lock scope and shift the remaining sprints toward stabilization and launch instead of continuing to add new functionality.

2. Sprint Planning Agenda

The following agenda was used to prepare for Sprint 7 planning:

- Context and goal of the meeting

- Review of Sprint 6 outcomes and completed work

- Review of current project milestones

- Review of updated project backlog

- Define Sprint 7 priorities

- Review and confirm Sprint 7 backlog items

- Break user stories into actionable tasks

- Review risks and feasibility

- Assign user stories and tasks

- Confirm acceptance criteria and test scenarios

- Discuss feature freeze timing with the Product Owner

- Obtain agreement from the Product Owner

3. Sprint Goal

Finish the Expo migration and get a working Android build running, continue hardening the backend and expanding test coverage across both platforms, and move App Store prep to completion while starting Play Store prep and B2B dashboard discovery. By the end of Sprint 7 the app should be running on both iOS and Android from a single codebase, with launch prep underway on both storefronts.

4. Project Epics

No new epics were added this sprint. Sprint 7 work continues across the six epics established during reactivation:

- Authentication and Account System

- Mobile App Foundation and Core UX

- Research, Integration, and Technical Validation

- Release Engineering and Deployment

- Quality Assurance and Testing

- B2B Partner Platform

5. Sprint Backlog Items

User Story 1

As a SAVR development team, we want the Expo migration finished and a working Android build running so that the app is truly cross platform from a single codebase.

- Priority: Critical

- Epic: Mobile App Foundation and Core UX

- Assigned To: Peter Forbes

- Effort: 12 points

- Current Status: New

Tasks

- Task 1: Finish migrating any remaining screens into Expo

  - Description: Close out the last of the screen migration work identified in the Sprint 6 audit so the app is fully running on Expo with no screens left on the old structure.

  - Expected Effort: 3

  - Assigned To: Peter Forbes

  - Status: New

- Task 2: Resolve the Android blockers identified in the Sprint 6 audit

  - Description: Work through the list of platform specific issues found during the Sprint 6 Android audit and resolve them one at a time.

  - Expected Effort: 4

  - Assigned To: Peter Forbes

  - Status: New

- Task 3: Get a working Android build compiling and running

  - Description: Produce a build that installs and runs on an Android device or emulator using the shared build configuration set up in Sprint 6.

  - Expected Effort: 3

  - Assigned To: Peter Forbes

  - Status: New

- Task 4: Fix cross platform UI inconsistencies found on Android

  - Description: Identify and correct layout, spacing, or styling issues that only show up on Android so the app looks consistent across both platforms.

  - Expected Effort: 2

  - Assigned To: Peter Forbes

  - Status: New

Test Scenarios

- The app runs entirely on Expo with no remaining screens on the old SwiftUI only structure.

- The Android build installs and launches without crashing.

- Core flows including authentication, chat, and lists work correctly on Android.

- UI renders consistently between iOS and Android for the same screens.

Test Acceptance Criteria

- 100% of app screens are running in Expo with no remaining SwiftUI only screens.

- The Android build installs and runs successfully on at least one physical device or emulator.

- At least 5 core flows are verified working on Android with no crashes.

- All blockers identified in the Sprint 6 audit are resolved or explicitly documented if deferred.

- No major visual inconsistencies remain between the iOS and Android versions of the same screens.

Status of Test Criteria

- Full Expo migration check: Not started

- Android build validation: Not started

- Core flow testing on Android: Not started

- Cross platform UI review: Not started

User Story 2

As a SAVR mobile user, I want the backend hardened and test coverage expanded across both platforms so that the app is stable and reliable heading into launch.

- Priority: High

- Epic: Quality Assurance and Testing / Research, Integration, and Technical Validation

- Assigned To: Aashir Javed

- Effort: 11 points

- Current Status: New

Tasks

- Task 1: Expand testing environment coverage to the remaining core flows

  - Description: Extend the testing environment set up in Sprint 6 to cover flyers, stores, and profile in addition to authentication, chat, and lists.

  - Expected Effort: 3

  - Assigned To: Aashir Javed

  - Status: New

- Task 2: Validate backend behavior against the Android build

  - Description: Confirm that the same backend endpoints and data return correctly when called from the Android build, not just iOS.

  - Expected Effort: 3

  - Assigned To: Aashir Javed

  - Status: New

- Task 3: Harden backend stability and error handling ahead of launch

  - Description: Review error handling, timeouts, and edge cases in the backend integration layer to reduce the chance of crashes or bad states once the app is live.

  - Expected Effort: 3

  - Assigned To: Aashir Javed

  - Status: New

- Task 4: Triage and fix bugs surfaced by the expanded test coverage

  - Description: Work through whatever issues the expanded testing environment turns up and fix the highest priority ones.

  - Expected Effort: 2

  - Assigned To: Aashir Javed

  - Status: New

Test Scenarios

- Testing environment produces results for flyers, stores, and profile in addition to the flows already covered.

- Backend calls made from the Android build return the same correct data as iOS.

- The app handles network failures and bad responses without crashing.

- Bugs found during testing are resolved and re-verified.

Test Acceptance Criteria

- Testing environment covers at least 6 core flows across both platforms.

- Backend responses are verified as consistent between iOS and Android for at least 4 key endpoints.

- The app does not crash under at least 3 tested failure conditions such as no network or a slow response.

- At least 5 bugs surfaced during this sprint are resolved and verified fixed.

- No new regressions are introduced into previously working backend flows.

Status of Test Criteria

- Expanded coverage validation: Not started

- Cross platform backend validation: Not started

- Failure condition testing: Not started

- Bug fix verification: Not started

User Story 3

As a SAVR mobile user, I want the App Store and Play Store presence finished and the B2B dashboard direction defined so that launch prep is complete and future work is scoped correctly.

- Priority: Medium-High

- Epic: Release Engineering and Deployment / B2B Partner Platform

- Assigned To: Alex Wei

- Effort: 10 points

- Current Status: New

Tasks

- Task 1: Finalize the App Store submission assets

  - Description: Complete and lock in the screenshots, icon set, and listing copy that were started in Sprint 6 so they are ready for submission.

  - Expected Effort: 3

  - Assigned To: Alex Wei

  - Status: New

- Task 2: Prepare Play Store listing assets and requirements

  - Description: Put together the Android equivalent of the App Store assets, including screenshots sized for Play Store and the listing metadata.

  - Expected Effort: 3

  - Assigned To: Alex Wei

  - Status: New

- Task 3: Run a B2B dashboard discovery session with the sponsor

  - Description: Meet with the Product Owner to understand what the B2B dashboard actually needs to do before any design or build work starts.

  - Expected Effort: 2

  - Assigned To: Alex Wei

  - Status: New

- Task 4: Draft initial B2B dashboard wireframes based on discovery

  - Description: Turn the discovery conversation into a first pass of wireframes so there is a starting point for later sprints.

  - Expected Effort: 2

  - Assigned To: Alex Wei

  - Status: New

Test Scenarios

- App Store assets are complete and meet Apple's size and format requirements.

- Play Store assets are complete and meet Google's size and format requirements.

- Discovery session produces clear, written requirements for the B2B dashboard.

- Wireframes reflect what was discussed in the discovery session.

Test Acceptance Criteria

- App Store assets are finalized and ready for submission with no missing pieces.

- Play Store assets are produced at the correct resolutions and cover all required fields.

- B2B discovery session is completed and documented with at least 5 concrete requirements or goals.

- At least 3 initial wireframe screens are produced for the B2B dashboard.

- The Product Owner confirms the discovery notes accurately reflect what they asked for.

Status of Test Criteria

- App Store asset review: Not started

- Play Store asset review: Not started

- Discovery session review: Not started

- Wireframe review: Not started

6. Task Breakdown and Assignment

Tasks were assigned based on the same ownership carried over from Sprint 6, since each person is closest to their own area:

- Peter Forbes owns finishing the Expo migration and getting Android running, since he has led migration work since Sprint 3 and completed the blocker audit in Sprint 6.

- Aashir Javed owns backend hardening and expanded test coverage, continuing directly from the testing environment work started in Sprint 6.

- Alex Wei owns finishing App Store prep, starting Play Store prep, and running B2B discovery, extending his release focused work from Sprint 6 into the next storefront and the B2B conversation.

Current task distribution: Peter 4 tasks, Aashir 4 tasks, Alex 4 tasks.

This keeps the workload even across the team and satisfies the rubric expectation of 3 to 5 tasks per member.

7. Effort Estimation

The effort estimates for Sprint 7 are:

- User Story 1 (Peter): 12 points

- User Story 2 (Aashir): 11 points

- User Story 3 (Alex): 10 points

Total Sprint Points: 33 points

This is a modest increase over the 30 points completed in Sprint 6. Since Sprint 6 finished in full and the team has a clearer picture of what is left on both the migration and backend sides, 33 points is a realistic step up rather than a big jump. Peter carries the most points this sprint because getting Android running is the hardest and most uncertain piece of work, while Aashir and Alex's stories are more predictable extensions of work already in progress.

8. Progress Tracking and Status Updates

Sprint 7 progress is tracked in Taiga and updated throughout the sprint.

Current board setup includes:

- User stories: 3

- Tasks: 12

- Epics: 6

- Status categories: New, In Progress, Ready for Test, Closed

Each user story and task is updated during standups and after meaningful progress so the board reflects real status throughout the sprint.

9. Risk Management

Risk 1: Android surfaces issues beyond the Sprint 6 audit

- Likelihood: Medium

- Impact: High

- Description: The Sprint 6 audit identified known blockers, but getting an actual build running often surfaces problems that only show up once you try. Android could take longer than the 12 points suggest.

- Mitigation Strategy: Tackle the highest risk blockers first instead of working through the list in order, so if something takes longer than expected it does not block the whole story at the end of the sprint.

Risk 2: Backend behaves differently on Android than iOS

- Likelihood: Medium

- Impact: Medium

- Description: The backend integration was built and tested against iOS first. There is a chance something behaves differently when called from the Android build, especially around networking or storage.

- Mitigation Strategy: Validate backend calls from Android as soon as a build exists rather than waiting until the end of the sprint to check.

Risk 3: Expanded testing reveals a larger bug backlog than expected

- Likelihood: Medium

- Impact: Medium

- Description: Extending test coverage to flyers, stores, and profile could turn up more issues than the sprint has room to fix.

- Mitigation Strategy: Triage bugs by severity as they come in and only commit to fixing the highest priority ones this sprint, carrying the rest forward instead of trying to fix everything at once.

Risk 4: App Store or Play Store guidelines cause rework

- Likelihood: Medium

- Impact: Medium

- Description: This is the first time the team is preparing assets for either store. There is a real chance something does not meet spec and has to be redone.

- Mitigation Strategy: Check assets against the official Apple and Google guidelines before considering them final, rather than after submission.

Risk 5: B2B discovery expands beyond scope

- Likelihood: Low

- Impact: Medium

- Description: Once the sponsor starts talking through what he wants for the B2B dashboard, there is a risk the conversation turns into an expectation of actual build work this sprint, which is not the plan.

- Mitigation Strategy: Set expectations with the Product Owner at the start of the discovery session that this sprint is requirements and wireframes only, not implementation.

Risk Monitoring Plan

- Review sprint risks during standups

- Log blockers in Taiga as sprint issues when they appear

- Get an Android build running early in the sprint so remaining issues are known with time to address them

- Revisit the feature freeze conversation with the Product Owner once Android is confirmed working

10. Notes on Project Management Software

All Sprint 7 backlog items, tasks, assignments, statuses, and priorities are documented in Taiga. The sprint board reflects:

- user stories tied to the sprint goal

- assigned tasks for each team member

- effort points

- status updates

- backlog alignment with all six project epics

This supports transparency, accountability, and continuous sprint tracking throughout Sprint 7.

Thank you.